## ACU Cost
Angular 9 → 20 migration — Devin ACU cost (AIDLC)
Rate: $2.25 per ACU
Session: https://infosys.devinenterprise.com/sessions/b089339539c84cfb8fe4913619e49d66
Pull request: https://github.com/infosys-training/angular2-hn/pull/35
Unit | AIDLC task | Start (UTC) | End (UTC) | Duration (s) | ACUs | Cost (USD)
A1-A3 | Inception: read repo config, BRD, units of work + acceptance criteria | 17:06:16 | 17:09:20 | 184 | 1.7528 | 3.94
B1 | Angular 9 -> 10 (npm package manager, headless karma launcher) | 17:09:20 | 17:11:16 | 116 | 1.105 | 2.49
B2 | Angular 10 -> 11 (+ first unit specs, legacy-peer-deps) | 17:11:16 | 17:13:00 | 104 | 0.9907 | 2.23
B3 | Angular 11 -> 12 | 17:13:00 | 17:14:13 | 73 | 0.6954 | 1.56
C1 | RxJS 7 imports, drop rxjs-compat, sass math.div | 17:14:13 | 17:15:20 | 67 | 0.6382 | 1.44
B4 | Angular 12 -> 13 | 17:15:20 | 17:16:04 | 44 | 0.4191 | 0.94
C5 | TSLint/codelyzer -> angular-eslint + fix violations | 17:16:04 | 17:17:18 | 74 | 0.7049 | 1.59
B5 | Angular 13 -> 14 | 17:17:18 | 17:18:12 | 54 | 0.5144 | 1.16
B6 | Angular 14 -> 15 (+ Protractor removal) | 17:18:12 | 17:19:17 | 65 | 0.6192 | 1.39
B7 | Angular 15 -> 16 | 17:19:17 | 17:20:04 | 47 | 0.4477 | 1.01
B8 | Angular 16 -> 17 | 17:20:04 | 17:20:52 | 48 | 0.4573 | 1.03
B9 | Angular 17 -> 18 | 17:20:52 | 17:21:41 | 49 | 0.4668 | 1.05
C9+B10 | Standalone migration, provideRouter/provideServiceWorker bootstrap, Angular 19 | 17:21:41 | 17:24:14 | 153 | 1.4575 | 3.28
B11+C6-C8 | Angular 20, application builder, control flow, inject(), Playwright e2e, ops config | 17:24:14 | 17:28:09 | 235 | 2.2386 | 5.04
E1-E2 | AIDLC prompt-prefix generator, cost tooling, final unit status | 17:28:09 | 17:30:54 | 165 | 1.5718 | 3.54
D-PR | PR #35 creation and summary | 17:30:54 | 17:31:52 | 58 | 0.5525 | 1.24
V1 | Post-PR verification (prod build, service worker/manifest serve check), test plan, testing handoff | 17:42:54 | 17:52:44 | 590 | 5.6204 | 12.65
Total | Angular 9 → 20 migration

## Summary
Metric | Value
Repository | infosys-training/angular2-hn
Session | https://infosys.devinenterprise.com/sessions/b089339539c84cfb8fe4913619e49d66
Pull request | https://github.com/infosys-training/angular2-hn/pull/35
Metric type | ACU (Agent Compute Unit)
Source | Devin session API: acu_consumption_at_last_user_interaction events + session acus_consumed
ACUs at session start | 0
ACUs at end of migration work | 20.2524
Migration ACUs (measured) | 20.2524
Migration window (UTC) | 2026-08-28T17:06:16Z → 2026-08-28T17:52:44Z
Billable wall-clock (minutes) | 35.43
Price per ACU (USD) | 2.25
Total cost (USD) | 45.57
Attribution method | Session-level ACU total is measured. Per-task values are attributed pro rata by each task's wall-clock duration, using commit timestamps on branch devin/1787936828-ng9-to-ng20-migration as task boundaries. Devin does not expose per-task ACU counters.
Confidence | task rows are derived, not measured